## Key Stakeholders and Roles

### This section sets out the key stakeholders involved in delivering the Voice of Change (VoC) program, outlining their roles, responsibilities, selection criteria, and common risks along with practical mitigation strategies. Clear role definition and active engagement are essential for effective coordination and delivery. Each stakeholder group brings a distinct but complementary contribution to the program’s goal of equipping widows with the support, skills, and confidence to lead change in their communities. The risk strategies included here are drawn from prior implementation experience and are intended to help teams anticipate and manage challenges before they disrupt progress.

### Widow Groups

| Category | Details |
| --- | --- |
| Responsibilities | • Participate in weekly VoC sessions • Provide safe, confidential spaces for sharing • Implement social action projects • Support group trainers • Document group activities and outcomes |
| Selection Criteria | • Existence for more than one year • Legal registration and documentation • Unity and love among members • Commitment to weekly meetings • Willingness to sign MOU |
| Potential Risks | Group conflict affecting implementation Insufficient group attendance Lack of engagement with curriculum |
| Mitigation Strategies | Implement conflict resolution training for all group members Establish clear communication protocols and grievance procedures Conduct regular check-ins with group leadership to identify and address emerging conflicts Create an attendance incentive system that recognizes consistent participation Schedule meetings at times determined by group consensus to maximize convenience Implement a buddy system where members check in with each other before meetings Adapt curriculum to incorporate local contexts and relevant examples Use participatory methods that encourage active involvement Collect regular feedback on curriculum relevance and make necessary adjustments |

| Widow Trainers |  |
| --- | --- |
| Responsibilities | Lead weekly VoC trainings in their groups Attend VOC trainings and other relevant training Serve as community ambassadors for Nyanam Identify and refer widows needing counseling Report challenges to widow mentors |
| Selection Criteria | Age between 35-50 years Self-driven and dedicated Able to read and write Time-conscious and reliable Deep listening skills Regular group attendance (80%+) |
| Potential Risks | Insufficient facilitation skills Time constraints and competing priorities Difficulty handling sensitive topics |
| Mitigation Strategies | Provide comprehensive initial training with regular refresher sessions Create simplified facilitation guides with step-by-step instructions Implement a shadowing program where new trainers observe experienced facilitators Offer modest stipends to compensate for time commitment Develop flexible training schedules that accommodate seasonal variations in availability Train backup facilitators who can step in when primary trainers are unavailable Provide specialized training on trauma-informed approaches Establish clear referral pathways for cases requiring professional intervention Create support circles for trainers to process challenging experiences |

| Widow Mentors |  |
| --- | --- |
| Responsibilities | Provide mentorship and supervision to trainers Lead VOC training sessions for trainers Support data collection and monitoring Visit leadership circles to provide support Submit reports through Kobo Collect Provide recommendations for improvement |
| Selection Criteria | Successful completion of multiple VoC trainings Alignment with Nyanam's vision and mission Basic computing and WhatsApp skills Literacy in native language, Kiswahili, and English Active engagement in group activities |
| Potential Risks | Transportation challenges for site visits Digital literacy limitations affecting reporting Inconsistent mentorship quality |
| Mitigation Strategies | Provide transportation allowances or arrange shared transportation Group site visits geographically to maximize efficiency Develop alternative remote mentorship protocols for periods when travel is difficult Conduct targeted digital literacy training with hands-on practice Create user-friendly reporting templates with minimal text entry Establish a buddy system pairing digitally proficient mentors with those needing support Develop standardized mentorship guidelines and quality benchmarks Implement regular performance reviews with constructive feedback Facilitate peer learning exchanges among mentors to share best practices |

| Program Administrators |  |
| --- | --- |
| Responsibilities | Develop curriculum with insights from staff and widows Train VoC facilitators Supervise widow trainers and mentors Review weekly reports Address arising issues Assess performance of trainers and mentors Oversee monitoring and evaluation |
| Potential Risks | Ineffective management of multiple groups Poor communication with field teams Inadequate response to implementation challenges Inconsistent quality control |
| Mitigation Strategies | Implement a tiered management structure with clear lines of responsibility Utilize project management software to track activities across groups Establish regular coordination meetings to ensure alignment Create multiple communication channels (WhatsApp groups, email, phone) Schedule regular check-in calls with field teams Develop a communication protocol specifying frequency and methods Establish a rapid response protocol for addressing urgent issues Create a decision-making framework to guide timely interventions Maintain a flexible contingency budget for unexpected challenges Develop comprehensive quality assurance guidelines and checklists Conduct random spot checks and observations of program activities Implement a continuous improvement system based on regular quality reviews |

### Partner Organizations

| Partner Organisations |  |
| --- | --- |
| Responsibilities | Identify and nominate widow trainers Ensure trainers attend required training Support VoC multiplication in their groups Collaborate with Nyanam widow mentors Facilitate surveys and data collection Participate in progress meetings Contribute to VoC partnership toolkit development |
| Potential Risks | Misalignment of expectations and commitments Insufficient resources allocated to implementation Competing priorities affecting program quality Poor communication and coordination |
| Mitigation Strategies | Develop detailed partnership agreements with clearly defined roles and deliverables Conduct joint planning sessions at program inception to ensure shared understanding Schedule quarterly partnership reviews to address any emerging misalignments Clearly outline resource requirements in partnership agreements Develop shared resource mobilization strategies where appropriate Create a resource pooling mechanism among partners for critical program components Integrate VoC activities into partners' existing strategic plans Develop annual work plans with partners that account for their other commitments Establish minimum quality standards that must be maintained regardless of other priorities Establish a partner coordination committee with regular meeting schedule Create a shared information management system accessible to all partners Designate specific liaison personnel responsible for inter-partner communication |